## Sheet1
Get to know the drone | fire it up, connect it, clone git, make a little commit, see if it still works
Add Seamus branch detection | integrate it ith the current drone
Test required accuracy | flight tests, what orientation offset is acceptable? | need optitrack for that
Test outdoors seamus
Choose and implement VIO
Test VIO | optitrack vs indoor vs outdoor comparison
Decide: full auto perching vs branch detection vs treevio
Adde branch detection close range sensors
Test and show improvement over original
Add obstacle avoidance
Full outdoor demo