## Sheet1
Thesis planning
Month | March |  |  |  | April |  |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  |  | August |  |  |  | September |  |  |  |  | October
Monday | 2024-03-04 | 2024-03-11 | 2024-03-18 | 2024-03-25 | 2024-04-01 | 2024-04-08 | 2024-04-15 | 2024-04-22 | 2024-04-29 | 2024-05-06 | 2024-05-13 | 2024-05-20 | 2024-05-27 | 2024-06-03 | 2024-06-10 | 2024-06-17 | 2024-06-24 | 2024-07-01 | 2024-07-08 | 2024-07-15 | 2024-07-22 | 2024-07-29 | 2024-08-05 | 2024-08-12 | 2024-08-19 | 2024-08-26 | 2024-09-02 | 2024-09-09 | 2024-09-16 | 2024-09-23 | 2024-09-30 | 2024-10-07 | 2024-10-14 | 2024-10-21 | 2024-10-28 | 2024-11-04 | 2024-11-11
until | bar: 2024-03-04 to 2024-11-11
Sunday | 2024-03-10 | 2024-03-17 | 2024-03-24 | 2024-03-31 | 2024-04-07 | 2024-04-14 | 2024-04-21 | 2024-04-28 | 2024-05-05 | 2024-05-12 | 2024-05-19 | 2024-05-26 | 2024-06-02 | 2024-06-09 | 2024-06-16 | 2024-06-23 | 2024-06-30 | 2024-07-07 | 2024-07-14 | 2024-07-21 | 2024-07-28 | 2024-08-04 | 2024-08-11 | 2024-08-18 | 2024-08-25 | 2024-09-01 | 2024-09-08 | 2024-09-15 | 2024-09-22 | 2024-09-29 | 2024-10-06 | 2024-10-13 | 2024-10-20 | 2024-10-27 | 2024-11-03 | 2024-11-10 | 2024-11-17
xPrize - Zürich Testing | bar: 2024-03-17 to 2024-03-24
xPrize - Brazil Testing | bar: 2024-04-14 to 2024-04-21
Literature Study | bar: 2024-03-31 to 2024-04-07; 2024-04-28 to 2024-05-05
- implement & check branch detection accuracy (optitrack) | bar: 2024-03-31
- write up on LS, prepare xPrize Brazil | bar: 2024-04-07
- write up LS, nothing else | bar: 2024-04-28
- finish LS, choose V(I)O | bar: 2024-05-05 to 2024-06-16
Setup ROS environment (based on previous perching drone) | 2024-06-30: get drone and build it
Implement VisualOdometry | 2024-06-30: make simulation work; 2024-08-04: =+ also vio; 2024-08-25: make work in May
- create odometry pose topic, get video in, create base structure | 2024-06-30: improve seamus work in june
- get keyframes working, pipeline VO ready | 2024-06-30: --> detect multiple branches and choose the right one
- VO ready, tested by translatring rotating camera by hand + optitrack | 2024-06-30: make 'trunk' with different multiple branches in june
Implement Camera-in-View Cost Function | bar: 2024-06-16 to 2024-06-30
- write own controller | bar: 2024-06-16
- add own controller with cost function | bar: 2024-06-23
- subscribe to pose topic and update/set cost function goal accordingly | bar: 2024-06-30
xPrize - Finals Preparation/Training | bar: 2024-07-07
xPrize - Finals Brazil | bar: 2024-07-14 to 2024-07-28
Vacation family | bar: 2024-08-04
Compile & run ROS on drone | 2024-06-30: make the planning, around 1 month, probs more
- run ros onboard, do flight checks | 2024-06-30: improve the gripper, change approach, eg at top?
- connect ROS to PX4 | 2024-06-30: in simulation,
Implement Visual-Inertial-Odometry on drone | 2024-06-30: real world testing in cyberzoo in september
- subscribe to IMU pose data, fuse V+I | 2024-06-30: det, branches, gripper update, planning (minco is nice)
- compile and test VIO with Optitrack | bar: 2024-09-15
Test & improve | bar: 2024-09-22 to 2024-10-06
- pose error mitigation | bar: 2024-09-22
- test indoors (both VIO and only VO-swinging branch) | bar: 2024-09-29
- test outdoors | bar: 2024-10-06
Write up Thesis (long vs short version?) | bar: 2024-06-09; 2024-06-30; 2024-09-01; 2024-09-22 to 2024-10-20